## Slide 1: Risk Management
1
Novel configuration
20
12
2
DOC target missed
16
12
3
Tech not ready by design freeze
12
8
4
Airport compatibility
12
8
5
Weight underestimate
12
9
Score = Likelihood x Consequence, each 1 to 5
Before mitigation
1
1
2
2
3
3
4
4
5
5
Consequence
1
2
3
4
5
After mitigation
1
1
2
2
3
3
4
4
5
5
Consequence
1
2
3
4
5
Likelihood
Identify
Rate
Mitigate
Monitor
Where risks come from
The brief
Regulations
2040 EIS
Our own limits
6
Performance shortfall
16
12
7
CS-25 non-compliance
15
10
8
Noise & emissions
12
8
6
6
7
7
8
8
9
Production ramp-up
16
9
10
Composite recycling
6
4
9
9
10
10

## Slide 2: Risks: Design
1 Novel configuration
“When analysing any configuration, consider both the benefits and risks … especially those which may become showstoppers.”
Airbus task introduction
Conventional
lower fuel gain
Blended wing
stability, 90 s evacuation
Flying V
stability, gate fit
Plan: screen each concept, keep a conventional fallback
3 Technology readiness
The technology has to be mature at design freeze, years before 2040 entry into service. If it slips, the fuel-burn gain goes with it.
Today
2026
Design freeze
before 2040
In service
2040
Fuel-burn gains a concept might rely on
≈10 %
engine
3–10 %
wing
8.2 %
hybrid assist
Plan: readiness check each review, mature-tech baseline
5 Weight underestimate
Extra weight needs a bigger wing and engines, which add more weight. The brief's margins may not cover real growth.
Evaluation MWE (Appendix 2)
Basic × 1.015 × 1.020
≈ +3.5 % after customer changes and conservatism
+1 t → +0.5–0.7 %
fuel burn per tonne of extra weight
Plan: track weight against the allowance each review

## Slide 3: Risks: Operation
2 DOC target missed
Fuel is the largest share of DOC (about 25–40 %), and the brief prices SAF a third above kerosene.
Chart: Fuel price, $ per US gal
| 2020 competitor (kerosene) | Our aircraft (100 % SAF)
Fuel price ($ per US gal) | 3 | 4
−25 %
gallons per seat-NM needed just to hold fuel cost level
3 ÷ 4 = 0.75
Plan: fuel-burn target from the DOC model now. DOC is a target: the brief does not mark designs down for missing it (4.12).
4 Airport compatibility
More span means less induced drag and fuel burn, but the aircraft must still fit existing gates and runways.
Example: Boeing 777X
Wing unfolded 71.8 m
Tips folded 64.8 m
0
20
40
60
80
Wingspan (m)
Code E gate < 65 m
Code F runway < 80 m
Plan: folding tips as an option; check span against both limits at every iteration.

## Slide 4: Risks: Performance and Compliance
6 Performance shortfall
The aircraft misses its range or field-length targets through excess drag, too little thrust or weight growth.
Key performance requirements
5,000 NM
range
≤3,000 m
take-off
≤2,700 m
landing
Plan: Early aerodynamic analysis,
Apply Airbus margins and iterate wing and engine sizing
7 CS-25 compliance
Structural safety, system integration and emergency evacuation all have to be shown to comply.
Evacuation (CS 25.803)
90 s
to evacuate the aircraft using half the exits
Plan: CS-25 compliance matrix, early requirments verifications and design adjustments.
8 Noise & emissions
The engine choice has to meet the noise and emissions targets.
Targets
−25 EPNdB
noise, Stage 3 target
40 %
emissions margin, CAEP/6
Plan: early qualitative assessment, favour low-noise, low-NOx engine options
Not all risks can be eliminated at SRR,the rest are monitored and mitigated through PDR and CDR.
Notes: Walk through the top risks briefly, don't read the table. Key message: these come straight from the brief, so they show we've read and understood it.
Be upfront that we haven't chosen a concept, so concept-specific risks (e.g. gate span for a high-aspect-ratio wing, evacuation for a BWB) will be added once we select one. Noise & emissions and airport compatibility are also in the full register.
Limitations: we can't plan for or resolve everything at this stage. What we've done: requirements from CS-25, project broken down into a WBS and subteams so it's manageable.
Biggest overall risk: not fulfilling the brief, which means cost. Bridge: we've acknowledged the risks - next is how we make it a reality on a practical level, which leads into costs.

## Slide 5: Risks: Manufacture and Disposal
9 Production ramp-up and supply chain
Supply chain distruptions and compoent shortages could delay aircraft production, increasing programme costs. The Boeing 787 was delivered about three years late, partly through supply-chain problems.
Scale of the task
≈ 700
aircraft to break even (W. Europe)
≈ 3 yr
787 delivery delay
Plan: Assess supplier readiness, identify critical components and evaluate alternative sourcing strategies
10 composite recycling
Carbon fibre composite structures can be difficult to recycle economically, increasing end of lide processing costs and reducing material recovery
Design life and options
25 years
airframe life
≈ 10 %
lighter, recyclable thermoplastics
End of life: life extension, freighter conversion, component recovery and recycling
Plan: Evaluate recyclable themoplastic composites, repairability and material recovery methods during trade studies.